## Sheet1
School AWS Cloud IT Infrastructure Project Gantt Chart S275931
Project Phase | Task Name | Start Date | End Date | Assigned Stakeholders | Progress | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01
Pre Project Consultation | IT Consultation with School
Initiation | Write Project Charter
Initiation | Conduct Cloud Readiness Assessment
Initiation | Feasibility Study
Initiation | Define Scope
Initiation | Kick-Off Meeting
Planning | Create Project Management Plan
Planning | Create Financial Plan
Planning | Create Resource Plan
Planning | Create Quality Plan
Planning | Conduct Risk Assessment
Planning | Create Risk Management Plan
Planning | Create Acceptance Plan
Planning | Create Procurement Plan
Execution | Cast Project Vision and Team Leadership
Execution | Create Tasks
Execution | Brief Team Members on their Tasks
Execution | Plan and Design School Cloud IT System
Execution | Draw AWS Architectural Diagrams
Execution | Conduct AWS Cost Estimate
Execution | Set UP AWS Accounts for School IT Admins and Developers
Execution | Set Region to UK-London
Execution | Create School VPC
Execution | Create Private Subnets
Execution | Create Public Subnets
Execution | Configure Internet Gateways
Execution | Create IAM User Roles
Execution | Set Up and Configure School Firewall
Execution | Create EC2 Instance for School Website
Execution | Create EC2 Instance for Online Portal
Execution | Create EC2 Instance for School IT Systems
Execution | Set Up Cloud9 IDE on EC2 Instances
Execution | Install development software, IDEs, SDKs, Programming Languages, APIs and Docker onto EC2 instances
Execution | Set Up AWS CodeCommit Git Rrpository for Version Control and Development Backups
Execution | Create School Website S3 Bucket
Execution | Create S3 Glacier to Baack Up School Website
Execution | Create S3 Bucket for Online Portal
Execution | Create S3 Glacier to Back Up Online Portal
Execution | Create EBS Storage for Application and Softwre Files
Execution | Create S3 Glacier Backup for Application and Software Files
Execution | Create EBS Storage for Staff Files
Execution | Create S3 Glacier Backup for Staff Files
Execution | Create EBS Storage for Student Files
Execution | Create S3 Glacier Backup for Student Files
Execution | Create AWS RDS Database for School Database(s)
Execution | Create S3 Glacier to Back UP School Database(s)
Execution | Set Up AWS Elastic Container Registry (ECR) to Store School Cloud Software Containers
Execution | Set Up AWS Elastic Container Service to Host School Cloud Software Containers
Execution | Create School External Load Balancer
Execution | Create School Internal Load Balancer
Execution | Create School IT System Load Balancer
Execution | Set Up AWS CloudFormation
Execution | Set Up AWS CloudWatch
Execution | Set Up AWS Config
Execution | Set Up AWS Management Console
Execution | Set Up AWS Systems Manager - Incident Manager
Execution | Set Up AWS Patch Manager
Execution | Plan and Design School Website
Execution | Develop, Code and Debug School Website
Execution | Build School Website
Execution | Test School Website
Execution | Deploy and Release School Website
Execution | Plan and Design Online Portals
Execution | Develop, Code and Debug Online Portals
Execution | Build Online Portals
Execution | Test Online Portals
Execution | Deploy and Release Online Portals
Execution | Plan and Design IT Administration Software
Execution | Develop, Code and Debug IT Administration Software
Execution | Build Online IT Administration Software
Execution | Test Online IT Administration Software
Execution | Plan and Design File Management System
Execution | Develop, Code and Debug File Management System
Execution | Build File Management System
Execution | Test File Management System
Execution | Plan and Design Communications System
Execution | Develop, Code and Debug Communications System
Execution | Build Communications Systemm
Execution | Test Communications System
Execution | Plan and Design School Administration Software
Execution | Develop, Code and Debug School Administration Software
Execution | Build School Administration Software
Execution | Test School Administration Software
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution
Execution